## masterlist_log
PROJE KODU | PROJE ADI | MÜŞTERİ | Tip | WBS Code | Origin | Shipment ID | No | HS Code (GTIP) | Malzeme Tanımı | Material Description | Qty 1 | Unit 1 | Qty 2 | Unit 2 | Unit Weight (kg) | Length (mm) | Width (mm) | Height-Thickness (mm) | Total Weight (kg) | Total Lenght (m) | Vendor | Deliverable Type | Cargo Group | Package Type | Package Qty | Package No | Net Weight (kg) | Gross Weight (kg)
VMP-S01064 | ATP_5000m3_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 1 |  | 12x1500x8000 mm ST37 Sac |  | 136 | pcs |  |  | 1130.33 | 8000 | 1500 | 12 | 153724.88 | - | ABC METAL |  | BT_steel_plates | Loose
VMP-S01065 | ATP_5000m3_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 2 |  | 12x1500x6900 mm ST37 Sac |  | 80 | pcs |  |  | 974.94 | 6900 | 1500 | 12 | 77995.2 | - | ABC METAL |  | BT_steel_plates | Loose
VMP-S01066 | ATP_5000m3_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 3 |  | 10x1500x6900 mm ST37 Sac |  | 80 | pcs |  |  | 812.44 | 6900 | 1500 | 10 | 64995.2 | - | ABC METAL |  | BT_steel_plates | Loose
VMP-S01067 | ATP_5000m3_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 4 |  | 8x1500x6900 mm ST37 Sac |  | 80 | pcs |  |  | 649.95 | 6900 | 1500 | 8 | 51996 | - | ABC METAL |  | BT_steel_plates | Loose
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main | 3.1.9 | İSKENDERUN | iskSHT_shp1 | 5 |  | 8x1500x6000 mm St37 Sac |  | 18 | pcs |  |  | 565.44 | 6000 | 1500 | 8 | 10177.92 | - | ABC METAL |  | ST_steel_plates | Loose
VMP-S01068 | ATP_5000m3_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 6 |  | 6x1500x6900 mm ST37 Sac |  | 120 | pcs |  |  | 487.49 | 6900 | 1500 | 6 | 58498.8 | - | ABC METAL |  | BT_steel_plates | Loose
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main | 3.1.10 | İSKENDERUN | iskSHT_shp1 | 7 |  | 6x1500x6000 mm St37 Sac |  | 12 | pcs |  |  | 423.75 | 6000 | 1500 | 6 | 5085 | - | ABC METAL |  | ST_steel_plates | Loose
VMP-S01069 | ATP_5000m3_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 8 |  | 4x1500x8000 mm ST37 Sac |  | 136 | pcs |  |  | 376.8 | 8000 | 1500 | 4 | 51244.8 | - | ABC METAL |  | BT_steel_plates | Loose
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 9 |  | 4x1500x6000 mm St37 Sac |  | 8 | pcs |  |  | 282.63 | 6000 | 1500 | 4 | 2261.04 | - | ABC METAL |  | ST_steel_plates | Loose
VMP-S01070 | ATP_5000m3_Bingazi | ATP | Main | 3.1.2 | İSKENDERUN | iskSHT_shp1 | 10 |  | 3x1500x8000 mm ST37 Sac |  | 136 | pcs |  |  | 282.63 | 8000 | 1500 | 3 | 38437.68 | - | ABC METAL |  | BT_steel_plates | Loose
VMP-S01071 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | KARABÜK | karabükRM_shp3 | 11 |  | 240 NPI 6mt |  | 192 | pcs |  |  | 216 | 6000 | 106 | 240 | 41472 | 1152 | MC METAL |  | BT_material | Bundle
VMP-S01071 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | KARABÜK | karabükRM_shp3 | 11 |  | 240 NPI 12mt |  | 96 | pcs |  |  | 432 | 6000 | 106 | 240 | 41472 | 576 | MC METAL |  | BT_material | Bundle
VMP-S01072 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | KARABÜK | karabükRM_shp3 | 12 |  | 180 NPI 6 mt |  | 60 | pcs |  |  | 131.4 | 6000 | 82 | 180 | 7884 | 360 | MC METAL |  | BT_material | Bundle
VMP-S01072 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | KARABÜK | karabükRM_shp3 | 12 |  | 180 NPI 12 mt |  | 30 | pcs |  |  | 264 | 6000 | 82 | 180 | 7920 | 180 | MC METAL |  | BT_material | Bundle
VMP-S01073 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | KARABÜK | vimpoRM_shp4 | 13 |  | 80 NPI 6 mt |  | 100 | pcs |  |  | 35.64 | 6000 | 42 | 80 | 3564 | 600 | MC METAL |  | BT_material | Bundle
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main | 3.4 | ANKARA | vimpoRM_shp4 | 14 |  | 80 NPI 6mt |  | 36 | pcs |  |  | 35.64 | 6000 | 42 | 80 | 1283.04 | 216 | MC METAL |  | ST_material | Bundle
VMP-S01074 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | ANKARA | vimpoRM_shp4 | 15 |  | 60x40x2 mm Kutu Profil |  | 600 | pcs |  |  | 18.08 | 6000 | 40 | 60x2 | 10848 | 3600 | MC METAL |  | BT_material | Bundle
VMP-S01075 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | ANKARA | vimpoRM_shp4 | 16 |  | 40x20x2 mm Kutu Profil |  | 200 | pcs |  |  | 10.55 | 6000 | 20 | 40x2 | 2110 | 1200 | MC METAL |  | BT_material | Bundle
VMP-S01077 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | ANKARA | vimpoRM_shp4 | 17 |  | 30x3 mm Silme 6 mt |  | 840 | pcs |  |  | 4.24 | 6000 | 30 | 3 | 3561.6 | 5040 | MC METAL |  | BT_material | Bundle
VMP-S01078 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | ANKARA | vimpoRM_shp4 | 18 |  | 50x5 mm Silme 6 mt |  | 96 | pcs |  |  | 11.78 | 6000 | 50 | 5 | 1130.88 | 576 | MC METAL |  | BT_material | Bundle
VMP-S01081 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | ANKARA | vimpoRM_shp4 | 19 |  | 50x50x5 mm Köşebent |  | 40 | pcs |  |  | 22.37 | 6000 | 50 | 50x5 | 894.8 | 240 | MC METAL |  | BT_material | Bundle
VMP-S01083 | ATP_5000m3_Bingazi | ATP | Main | 3.4 | ANKARA | vimpoRM_shp4 | 20 |  | 10x50 lama 6 mt |  | 60 | pcs |  |  | 23.55 | 6000 | 50 | 10 | 1413 | 360 | MC METAL |  | BT_material | Bundle
VMP-S01076 | ATP_5000m3_Bingazi | ATP | Main | 3.2.2 | ADANA | adanaPPS_shp2 | 21 |  | 1" 2 mm dikişli boru 6 mt |  | 312 | mt |  |  | 2.19 | [5 empty] | NORM BORU |  | BT_pipe
VMP-S01079 | ATP_5000m3_Bingazi | ATP | Main | 3.2.2 | ADANA | adanaPPS_shp3 | 22 |  | 8'' 4 mm dikişli boru 6 mt |  | 120 | mt |  |  | 118.4 | [5 empty] | NORM BORU |  | BT_pipe
VMP-S01087 | ATP_5000m3_Bingazi | ATP | Main | 3.2.2 | ADANA | adanaPPS_shp4 | 23 |  | 2" 60,30x3,2 mm P235GH-TC1 çelik çekme boru 12mt |  | 10500 | mt | [8 empty] | NORM BORU |  | BT_pipe
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main | 3.2.2 | ADANA | adanaPPS_shp5 | 24 |  | 8'' 4 mm dikişli boru 6 mt |  | 24 | mt | [6 empty] | 509 |  | NORM BORU |  | ST_pipe
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main | 3.2.2 | ADANA | adanaPPS_shp6 | 25 |  | 2" 3,2 mm çelik çekme boru P235GH |  | 800 | mt | [6 empty] | 3590 |  | NORM BORU |  | ST_pipe
VMP-S01080 | ATP_5000m3_Bingazi | ATP | Main |  | ANKARA |  | 17 |  | Baklavalı sacdan basamak-ÇİZİM VAR-DAR TARAFA 8" BORUYA GÖRE KAYNAK AĞIZLI |  | 220 | pcs | [8 empty] | BAYDOĞANLAR |  | BT_material
VMP-S01082 | ATP_5000m3_Bingazi | ATP | Main |  | ANKARA |  | 19 |  | ETEK SACI - 3x100x2000 mm St37 sac |  | 140 | pcs | [8 empty] | BAYDOĞANLAR |  | BT_material
VMP-S01088 | ATP_5000m3_Bingazi | ATP | Main |  | ANKARA |  | 25 |  | 2'' 180° Dirsek SCH40 |  | 840 | pcs |  |  | 1.8 | [5 empty] | TARGET |  | BT_material
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 6 |  | 2'' 180° Dirsek SCH40 |  | 100 | pcs |  |  | 1.8 | [5 empty] | TARGET |  | BT_material
VMP-S01089 | ATP_5000m3_Bingazi | ATP | Main |  | ANKARA |  | 26 |  | Trapez Vidası 5,5X25 MM |  | 60 | kg |  |  | 60 |  |  |  | 60 |  | FT MAKİNE |  | BT_material
VMP-S01090 | ATP_5000m3_Bingazi | ATP | Main |  | ANKARA |  | 27 |  | Antipas boya 25 kg |  | 16 | can |  |  | 25 |  |  |  | 400 |  | FT MAKİNE |  | BT_material
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 1 |  | KAYNAKÇI ELDİVENİ |  | 180 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 2 |  | SARI MONTAJ ELDİVENİ BEYBİ |  | 300 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 3 |  | BAŞ MASKESİ |  | 10 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 4 |  | MASKE CAMI SİYAH |  | 100 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 5 |  | TAŞLAMA GÖZLÜĞÜ |  | 20 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 6 |  | 4*2,5 TTR KABLO 380 GRUP PRİZ 380 ERKEK 20 MT |  | 4 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 7 |  | 3*2,5 TTR KABLO 220 GRUP PRİZ 220 ERKEK 20 MT |  | 4 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 8 |  | ATLAS ATCK 105-10 TON 5 MT CARASKAL |  | 8 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 9 |  | 500 GR ÇEKİÇ |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 10 |  | 5 KG BALYOZ |  | 3 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 11 |  | İZELTAŞ 12 PRÇ ALLEN SETİ |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 12 |  | İZELTAŞ 160 MM YAN KESKİ |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 13 |  | İZELTAŞ DÜZ TORNAVİDA 5*150 |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 14 |  | İZELTAŞ KONTROL KALEMİ |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 15 |  | İZELTAŞ YILDIZ TORNAVİDA 4,5*150 |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 16 |  | İZELTAŞ 160 MM PENSE |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 17 |  | İZELTAŞ 500 MM LEVYE |  | 10 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 18 |  | İZELTAŞ 12 Lİ AÇIK AĞIZ ANAHTAR TKM |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 19 |  | İZELTAŞ 12 Lİ YILDIZ ANAHTAR TKM |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 20 |  | İZELTAŞ 1/2 BORU ANAHTARI |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 21 |  | İZELTAŞ 3 '' BORU ANAHTARI |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 22 |  | SELÜLOZİK TİNER |  | 4 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 23 |  | 25 CM RULO DEKOR |  | 4 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 24 |  | PARMAK RULO DEKOR |  | 15 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 25 |  | 8 MM BİTS LOKMA |  | 10 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 26 |  | BOSCH GSB 13 RE ELEKTRİKLİ MATKAP |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 27 |  | BOSCH GWS 750 TAŞLAMA |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 28 |  | EGESAN 230*3 KESME TAŞI |  | 125 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 29 |  | EGESAN 180*8 TAŞLAMA TAŞI |  | 150 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 30 |  | GÖNYE 35 CM |  | 3 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 31 |  | 3 TON PEHLİVAN KRİKO |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 32 |  | SU TERAZİSİ 60 CM MIKNATISLI |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 33 |  | BAĞ TELİ |  | 20 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 34 |  | TEFLON BANT |  | 10 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 35 |  | SİYAH ELEKTRİK BANDI |  | 20 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 36 |  | ŞERİT METRE 30 MT FİSCO |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 37 |  | ŞERİT METRE 5 MT FİSCO |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 38 |  | DUMAN EMİCİ FAN 4000-4500 M3 |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 39 |  | 100 W PROJEKTÖR LAMBA |  | 5 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 40 |  | KOMPRESÖR 16 BAR |  | 1 | pcs | [8 empty] | FT MAKİNE |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 38 |  | PANO-40 MT KABLO, 380 V Multi-Outlet Electrical Panel / Distribution Board |  | 3 | pcs | [8 empty] | TMC |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 39 |  | Kaynak Makinesi (Kartsız) Soyberg 250 A Trafolu (kartsız) 350-400A |  | 4 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 40 |  | 35 KAYNAK KABLOSU |  | 300 | mt | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 41 |  | KAYNAK PENSESİ 600 AMPER |  | 20 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 42 |  | ŞALAMA SET+LPG SAAT |  | 3 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 43 |  | LPG SAAT |  | 3 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 44 |  | OKSİJEN SAAT |  | 3 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 45 |  | MAVİ KIRMIZI HORTUM |  | 30 | mt | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 46 |  | JAKI 70-95 ERKEK |  | 15 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 47 |  | JAKI 70-95 DİŞİ |  | 15 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 48 |  | BAZİK ELEKTROD 4MM |  | 35100 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 40 |  | RUTİL ELEKTROD 4 MM |  | 10800 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 41 |  | BAZİK ELEKTROD 3,25 MM |  | 13500 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 42 |  | RUTİL ELEKTROD 3,25 MM |  | 12000 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 43 |  | BAZİK ELEKTROD 2,5 MM |  | 6000 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 44 |  | ELEKTROD FIRINI BMK1 1 PAKETLİK |  | 3 | pcs | [8 empty] | ESER TEKNİK |  | siteequipment
VMP-S01084 | ATP_5000m3_Bingazi | ATP | Main | 3.3.2 | KAYSERİ |  | 21 |  | 100 mm Taş Yünü Rabitz Telli en 1 mt boy 3 mt |  | 5840 | M² | 1946.6667 | pkg | 25 | 1000 | 63 | 63 | 48666.6667 |  | EDO |  | isolation | Roll
VMP-S01085 | ATP_5000m3_Bingazi | ATP | Main |  | ANKARA |  | 22 |  | BOYALI GALVANİZ FORMLU SAC DX51 Z50 Tek Taraf Polyester 15/5/5 Ral 9002 Film: Yok Form: 27/200 - 1040 Trapez Levh Kalınlık: 0.7 Boy:720 |  | 600 | pcs |  |  | 43 | 7200 | 1040 | 0.7 | 25800 |  | UMS |  | isolation | Loose
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | BATMAN |  | 37 |  | BÜYÜK SİLİNDİR MAKİNESİ 3x5 mt |  | 1 | pcs | [8 empty] | SEÇİLECEK |  | siteequipment
VMP-S01086 | ATP_5000m3_Bingazi | ATP | Main |  | BATMAN |  | 23 |  | EŞANJÖR(lazer kesim+talaşlı imalat+malzeme+işçilik) |  | 4 | pcs | [8 empty] | İLİHAN |  | BT_material
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 1 |  | HOT OIL BOILERS | HOT OIL BOILERS | 3 | pcs | [6 empty] | 20000 |  | VİMPO |  | boiler
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 1 |  | PLATFORM | PLATFORM | 1 | pcs | [6 empty] | 35000 |  | VİMPO |  | platform
VMP-S01064-2 | ATP_SITE_Bingazi | ATP | Main |  | ANKARA |  | 1 |  | CONTROL ROOM | CONTROL ROOM | 1 | pcs |  |  | 10000 | 11000 | 2200 | 2300 | 10000 | 11 | VİMPO |  | controlroom

## isk_shp1 (hidden)
Shipment ID | Container No | Malzeme 1 | Qty | Unit | Unit Weight (kg) | Total Weight (kg) | Malzeme 2 | Adet 2 | Malzeme 3 | Adet 3 | Malzeme 4 | Adet 4 | Toplam Cotainer Weight (kg) | Payload Dif (kg) | Durum
iskenderun_shp1 | C01 | 12x1500x8000 mm ST37 Sac | 23 | pcs | 1130.33 | 25997.59 | [6 empty] | 25997.59 | -2.41 | Limit Altı
iskenderun_shp1 | C02 | 12x1500x8000 mm ST37 Sac | 23 | pcs | 1130.33 | 25997.59 | [6 empty] | 25997.59 | -2.41 | Limit Altı
iskenderun_shp1 | C03 | 12x1500x8000 mm ST37 Sac | 23 | pcs | 1130.33 | 25997.59 | [6 empty] | 25997.59 | -2.41 | Limit Altı
iskenderun_shp1 | C04 | 12x1500x8000 mm ST37 Sac | 23 | pcs | 1130.33 | 25997.59 | [6 empty] | 25997.59 | -2.41 | Limit Altı
iskenderun_shp1 | C05 | 12x1500x8000 mm ST37 Sac | 23 | pcs | 1130.33 | 25997.59 | [6 empty] | 25997.59 | -2.41 | Limit Altı
iskenderun_shp1 | C06 | 10x1500x6900 mm ST37 Sac | 32 | pcs | 812.44 | 25998.08 | [6 empty] | 25998.08 | -1.92 | Limit Altı
iskenderun_shp1 | C07 | 10x1500x6900 mm ST37 Sac | 32 | pcs | 812.44 | 25998.08 | [6 empty] | 25998.08 | -1.92 | Limit Altı
iskenderun_shp1 | C08 | 8x1500x6900 mm ST37 Sac | 40 | pcs | 649.95 | 25998 | [6 empty] | 25998 | -2 | Sınırda
iskenderun_shp1 | C09 | 8x1500x6900 mm ST37 Sac | 40 | pcs | 649.95 | 25998 | [6 empty] | 25998 | -2 | Sınırda
iskenderun_shp1 | C10 | 4x1500x8000 mm ST37 Sac | 69 | pcs | 376.8 | 25999.2 | [6 empty] | 25999.2 | -0.8 | Limit Altı
iskenderun_shp1 | C11 | 12x1500x6900 mm ST37 Sac | 26 | pcs | 974.94 | 25348.44 | [6 empty] | 25998.39 | -1.61 | Limit Altı
|  | 8x1500x6900 mm ST37 Sac | 1 | pcs | 649.95 | 649.95
iskenderun_shp1 | C12 | 12x1500x6900 mm ST37 Sac | 26 | pcs | 974.94 | 25348.44 | [6 empty] | 25998.39 | -1.61 | Limit Altı
|  | 8x1500x6900 mm ST37 Sac | 1 | pcs | 649.95 | 649.95
iskenderun_shp1 | C13 | 12x1500x6900 mm ST37 Sac | 26 | pcs | 974.94 | 25348.44 | [6 empty] | 25998.39 | -1.62 | Limit Altı
|  | 8x1500x6900 mm ST37 Sac | 1 | pcs | 649.95 | 649.95
iskenderun_shp1 | C14 | 10x1500x6900 mm ST37 Sac | 16 | pcs | 812.44 | 12999.04 | [6 empty] | 25998.04 | -1 | Limit Altı
|  | 8x1500x6900 mm ST37 Sac | 20 | pcs | 649.95 | 12999
iskenderun_shp1 | C15 | 3x1500x8000 mm ST37 Sac | 89 | pcs | 282.63 | 25154.07 | [6 empty] | 26284.59 | 284.59 | Az Aşım
|  | 4x1500x6000 mm ST37 Sac | 4 | pcs | 282.63 | 1130.52
iskenderun_shp1 | C16 | 6x1500x6900 mm ST37 Sac | 53 | pcs | 487.49 | 25836.97 | [6 empty] | 26119.6 | 119.6 | Az Aşım
|  | 4x1500x6000 mm ST37 Sac | 1 | pcs | 282.63 | 282.63
iskenderun_shp1 | C17 | 4x1500x8000 mm ST37 Sac | 34 | pcs | 376.8 | 12811.2 | [6 empty] | 26094.81 | 94.81 | Az Aşım
|  | 3x1500x8000 mm ST37 Sac | 46 | pcs | 282.63 | 13000.98
|  | 4x1500x6000 mm ST37 Sac | 1 | pcs | 282.63 | 282.63
iskenderun_shp1 | C18 | 8x1500x6900 mm ST37 Sac | 17 | pcs | 649.95 | 11049.15 | [6 empty] | 25991.28 | -8.72 | Az Aşım
|  | 8x1500x6000 mm ST37 Sac | 18 | pcs | 565.44 | 10177.92
|  | 6x1500x6900 mm ST37 Sac | 9 | pcs | 487.49 | 4387.41
|  | 4x1500x8000 mm ST37 Sac | 1 | pcs | 376.8 | 376.8
iskenderun_shp1 | C19 | 6x1500x6900 mm ST37 Sac | 18 | pcs | 487.49 | 8774.82 | [6 empty] | 26200.05 | 200.05 | Az Aşım
|  | 6x1500x6000 mm ST37 Sac | 12 | pcs | 423.75 | 5085
|  | 4x1500x8000 mm ST37 Sac | 32 | pcs | 376.8 | 12057.6
|  | 4x1500x6000 mm ST37 Sac | 1 | pcs | 282.63 | 282.63
iskenderun_shp1 | C20 | 12x1500x8000 mm ST37 Sac | 21 | pcs | 1130.33 | 23736.93 | [6 empty] | 26252.07 | 252.07 | Az Aşım
|  | 12x1500x6900 mm ST37 Sac | 2 | pcs | 974.94 | 1949.88
|  | 3x1500x8000 mm ST37 Sac | 1 | pcs | 282.63 | 282.63
|  | 4x1500x6000 mm ST37 Sac | 1 | pcs | 282.63 | 282.63

## Container_Plan
Origin | Shipment ID | Container ID | Container Type | Material | Qty 1 | Unit 1 | Qty 2 | Unit 2 | Unit Weight (kg) | Total Weight (kg) | Total Container Weight (kg) | Payload Dif (kg) | Pos
İSKENDERUN | iskSHT_shp1 | C01 | 40OT | 6x1500x6900 St37 Sheet | 53 | pcs |  |  | 487.49 | 25836.97 | 25836.97 | -163.03 | Limit Altı
İSKENDERUN | iskSHT_shp1 | C02 | 40OT | 12x1500x8000 St37 Sheet | 22 | pcs |  |  | 1130.33 | 24867.26 | 25715.15 | -284.85 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 3 | pcs |  |  | 282.63 | 847.89
İSKENDERUN | iskSHT_shp1 | C03 | 40OT | 12x1500x8000 St37 Sheet | 22 | pcs |  |  | 1130.33 | 24867.26 | 25715.15 | -284.85 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 3 | pcs |  |  | 282.63 | 847.89
İSKENDERUN | iskSHT_shp1 | C04 | 40OT | 12x1500x8000 St37 Sheet | 22 | pcs |  |  | 1130.33 | 24867.26 | 25715.15 | -284.85 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 3 | pcs |  |  | 282.63 | 847.89
İSKENDERUN | iskSHT_shp1 | C05 | 40OT | 12x1500x8000 St37 Sheet | 22 | pcs |  |  | 1130.33 | 24867.26 | 25715.15 | -284.85 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 3 | pcs |  |  | 282.63 | 847.89
İSKENDERUN | iskSHT_shp1 | C06 | 40OT | 12x1500x8000 St37 Sheet | 22 | pcs |  |  | 1130.33 | 24867.26 | 25715.15 | -284.85 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 3 | pcs |  |  | 282.63 | 847.89
İSKENDERUN | iskSHT_shp1 | C07 | 40OT | 10x1500x6900 St37 Sheet | 31 | pcs |  |  | 812.44 | 25185.64 | 25750.9 | -249.1 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 2 | pcs |  |  | 282.63 | 565.26
İSKENDERUN | iskSHT_shp1 | C08 | 40OT | 10x1500x6900 St37 Sheet | 31 | pcs |  |  | 812.44 | 25185.64 | 25750.9 | -249.1 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 2 | pcs |  |  | 282.63 | 565.26
İSKENDERUN | iskSHT_shp1 | C09 | 40OT | 10x1500x6900 St37 Sheet | 16 | pcs |  |  | 812.44 | 12999.04 | 25998.04 | -1.96 | Limit Altı
|  |  |  | 8x1500x6900 St37 Sheet | 20 | pcs |  |  | 649.95 | 12999
İSKENDERUN | iskSHT_shp1 | C10 | 40OT | 8x1500x6900 St37 Sheet | 39 | pcs |  |  | 649.95 | 25348.05 | 25630.68 | -369.32 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 1 | pcs |  |  | 282.63 | 282.63
İSKENDERUN | iskSHT_shp1 | C11 | 40OT | 6x1500x6900 St37 Sheet | 52 | pcs |  |  | 487.49 | 25349.48 | 25632.11 | -367.89 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 1 | pcs |  |  | 282.63 | 282.63
İSKENDERUN | iskSHT_shp1 | C12 | 40OT | 4x1500x8000 St37 Sheet | 68 | pcs |  |  | 376.8 | 25622.4 | 25905.03 | -94.97 | Limit Altı
|  |  |  | 3x1500x8000 St37 Sheet | 1 | pcs |  |  | 282.63 | 282.63
İSKENDERUN | iskSHT_shp1 | C13 | 40OT | 12x1500x8000 St37 Sheet | 21 | pcs |  |  | 1130.33 | 23736.93 | 25969.44 | -30.56 | Limit Altı
|  |  |  | 12x1500x6900 St37 Sheet | 2 | pcs |  |  | 974.94 | 1949.88
|  |  |  | 4x1500x6000 St37 Sheet | 1 | pcs |  |  | 282.63 | 282.63
İSKENDERUN | iskSHT_shp1 | C14 | 40OT | 12x1500x6900 St37 Sheet | 25 | pcs |  |  | 974.94 | 24373.5 | 25588.71 | -411.29 | Limit Altı
|  |  |  | 8x1500x6900 St37 Sheet | 1 | pcs |  |  | 649.95 | 649.95
|  |  |  | 3x1500x8000 St37 Sheet | 2 | pcs |  |  | 282.63 | 565.26
İSKENDERUN | iskSHT_shp1 | C15 | 40OT | 12x1500x6900 St37 Sheet | 25 | pcs |  |  | 974.94 | 24373.5 | 25588.71 | -411.29 | Limit Altı
|  |  |  | 8x1500x6900 St37 Sheet | 1 | pcs |  |  | 649.95 | 649.95
|  |  |  | 3x1500x8000 St37 Sheet | 2 | pcs |  |  | 282.63 | 565.26
İSKENDERUN | iskSHT_shp1 | C16 | 40OT | 12x1500x6900 St37 Sheet | 25 | pcs |  |  | 974.94 | 24373.5 | 25588.71 | -411.29 | Limit Altı
|  |  |  | 8x1500x6900 St37 Sheet | 1 | pcs |  |  | 649.95 | 649.95
|  |  |  | 3x1500x8000 St37 Sheet | 2 | pcs |  |  | 282.63 | 565.26
İSKENDERUN | iskSHT_shp1 | C17 | 40OT | 6x1500x6900 St37 Sheet | 5 | pcs |  |  | 487.49 | 2437.45 | 25985.65 | -14.35 | Limit Altı
|  |  |  | 6x1500x6000 St37 Sheet | 12 | pcs |  |  | 423.75 | 5085
|  |  |  | 4x1500x8000 St37 Sheet | 49 | pcs |  |  | 376.8 | 18463.2
İSKENDERUN | iskSHT_shp1 | C18 | 40OT | 4x1500x8000 St37 Sheet | 16 | pcs |  |  | 376.8 | 6028.8 | 25812.9 | -187.1 | Limit Altı
|  |  |  | 4x1500x6000 St37 Sheet | 7 | pcs |  |  | 282.63 | 1978.41
|  |  |  | 3x1500x8000 St37 Sheet | 63 | pcs |  |  | 282.63 | 17805.69
İSKENDERUN | iskSHT_shp1 | C19 | 40OT | 8x1500x6900 St37 Sheet | 17 | pcs |  |  | 649.95 | 11049.15 | 25708.47 | -291.53 | Limit Altı
|  |  |  | 8x1500x6000 St37 Sheet | 17 | pcs |  |  | 565.44 | 9612.48
|  |  |  | 6x1500x6900 St37 Sheet | 9 | pcs |  |  | 487.49 | 4387.41
|  |  |  | 4x1500x8000 St37 Sheet | 1 | pcs |  |  | 376.8 | 376.8
|  |  |  | 3x1500x8000 St37 Sheet | 1 | pcs |  |  | 282.63 | 282.63
İSKENDERUN | iskSHT_shp1 | C20 | 40OT | 12x1500x8000 St37 Sheet | 5 | pcs |  |  | 1130.33 | 5651.65 | 25093.55 | -906.45 | Limit Altı
|  |  |  | 12x1500x6900 St37 Sheet | 3 | pcs |  |  | 974.94 | 2924.82
|  |  |  | 10x1500x6900 St37 Sheet | 2 | pcs |  |  | 812.44 | 1624.88
|  |  |  | 8x1500x6900 St37 Sheet | 1 | pcs |  |  | 649.95 | 649.95
|  |  |  | 8x1500x6000 St37 Sheet | 1 | pcs |  |  | 565.44 | 565.44
|  |  |  | 6x1500x6900 St37 Sheet | 1 | pcs |  |  | 487.49 | 487.49
|  |  |  | 4x1500x8000 St37 Sheet | 2 | pcs |  |  | 376.8 | 753.6
|  |  |  | 3x1500x8000 St37 Sheet | 44 | pcs |  |  | 282.63 | 12435.72
ADANA | adanaPPS_shp2 | C21 | 40OT | 2" 60,30x3,2 mm P235GH-TC1 çelik çekme boru L:11.9 mt | 5688 | mt | 474 | pcs | 4.57 | 25994.16 | 25994.16 | -5.84 | Limit Altı
ADANA | adanaPPS_shp2 | C22 | 40OT | 2" 60,30x3,2 mm P235GH-TC1 çelik çekme boru L:11.9 mt | 4812 | mt | 401 | pcs | 4.57 | 21990.84 | 25534.68 | -465.32 | Limit Altı
|  |  |  | 1" 2 mm dikişli boru 6 mt | 312 | mt | 134 | pcs | 1.56 | 486.72
|  |  |  | 8'' 4 mm dikişli boru 6 mt | 144 | mt | 52 | pcs | 21.23 | 3057.12
ADANA |  |  |  | 2" 60,30x3,2 mm çelik çekme boru P235GH 6 mt | 800 | mt | 24 | pcs | 4.49 | 3592
KARABÜK | karabükRM_ship3 | C23 | 40OT | 240 NPI 6mt | 80 | pcs | 480 | mt | 265 | 21200 | 26000 | 0 | Limit
|  |  |  | 180 NPI 6 mt | 30 | pcs | 180 | mt | 160 | 4800
KARABÜK | karabükRM_ship3 | C24 | 40OT | 240 NPI 6mt | 80 | pcs | 480 | mt | 265 | 21200 | 26000 | 0 | Limit
|  |  |  | 180 NPI 6 mt | 30 | pcs | 180 | mt | 160 | 4800
KARABÜK |  |  |  | 240 NPI 6mt | 32 | pcs |  |  | 265 | 8480 | 8480
|  |  |  | 80 NPI 6 mt | 136 | pcs | 816 | mt | 35.64 | 4847.04 | 24805.32 | -1194.68 | Limit Altı
ANKARA | vimpoRM_shp4 | C25 | 40OT | 60x40x2 mm Kutu Profil | 600 | pcs | 3600 | mt | 18.08 | 10848
|  |  |  | 40x20x2 mm Kutu Profil | 200 | pcs | 1200 | mt | 10.55 | 2110
|  |  |  | 30x3 mm Silme 6 mt | 840 | pcs | 5040 | mt | 4.24 | 3561.6
|  |  |  | 50x5 mm Silme 6 mt | 96 | pcs | 576 | mt | 11.78 | 1130.88
|  |  |  | 50x50x5 mm Köşebent | 40 | pcs | 240 | mt | 22.37 | 894.8
|  |  |  | 10x50 lama 6 mt | 60 | pcs | 360 | mt | 23.55 | 1413

## Shipment_View
Project | WBS Code | Deliverable Type | Shipment ID | Origin | Supplier | Cargo Group | Material | Description | Qty | Unit | Unit Weight (kg) | Total Weight (kg) | Length (m) | Width | Height | Package Type | Package Qty | HS Code (GTIP) | Notes

## Packing_List
Package No | Description | Qty | Net Weight | Gross Weight | Dimensions | HS Code